## Sheet1
Project Name: |  |  | Youth Development and Education Gantt Chart
Company Name: |  |  | Louisville Urban League
Date of Report: |  |  | 2011-02-17
Task Name | Start Date | End Date | Days Completed | Days Remaining | Duration | Member Responsibility | Task Dependencies
Analysis of I2 | 2011-02-07 | 2011-02-14 | 7 | 0 | 7 days? | All | N/A
Update Vision Document from I1 | 2011-02-14 | 2011-02-15 | 2 | 0 | 2 days? | All | I1 is complete
I2: | 2011-02-15 | 2011-02-21 | 3 | 4 | 7 days?
Gantt Chart | 2011-02-15 | 2011-02-15 | 1 | 0 | 1 day? | Leslie Dawson | I1 and I2 deliverables
Vision Document: | 2011-02-16 | 2011-02-18 | 2 | 1 | 3 days? | All
Risk and Feasibility Analysis | 2011-02-16 | 2011-02-18 | 2 | 1 | 3 days? | Leslie Dawson, Kelsi Jones
Use Cases | 2011-02-16 | 2011-02-17 | 2 | 0 | 2 days? | Kelli Fowler, Josh Wachsman
System Requirements | 2011-02-16 | 2011-02-17 | 2 | 0 | 2 days? | Kelli Fowler, Josh Wachsman
Prototypes (Student Enrollement, Satisfaction) | 2011-02-16 | 2011-02-16 | 1 | 0 | 1 day? | Kelli Fowler, Jake Ellis
Presentation: | 2011-02-16 | 2011-02-21 | 2 | 4 | 6 days? |  | I2 documentation complete
Design Presenation | 2011-02-16 | 2011-02-18 | 2 | 1 | 3 days? | Josh Wachsman
Practice Presentation and Review Notes | 2011-02-18 | 2011-02-21 | 0 | 3 | 3 days? | All | Presentation Complete

## Sheet2
40581
40595